## Ark1
WP5.2 workplan- resources | Responsible | Partners | Expected resources | KU-CST | KU-LAN | KU-INSS | DSL | DSN | AU | CBS | KB | SDU | NatMus
Opdateret 12/12/08, v2 |  |  | pm | pm | pm | pm | pm | pm | pm | pm | pm | pm | pm
Se også WP5.2_opgaver_detaljer.doc
Before T9
Task 0: Coordination (until T9) | CST | CST | 0.25 | 0.25
Task 1: Survey of partners’ existing resources. | CST | all | 1.4 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.1 | 0.1
Task 2: Analysis of metadata and technical solutions for text resources. | CST | CST,KB | 0.9 | 0.6 | [6 empty] | 0.3
Total until T9 |  |  | 2.55 | 1.25 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1
Before T18:
Task 0: Coordination (until T18) | CST | CST | 0.5 | 0.5
Task 3: Informe ourselves about progress in EU-CLARIN concerning metadata, standards and integration. Giving feedback when appropriate. | CST | CST,KB,DSL | 1.2 | 0.4 |  |  | 0.4 |  |  |  | 0.4
Task 4: Survey about resources and tools in DK, which is not owned/used by partners of DK-CLARIN. Survey about partners existing tools | CST | all | 1.3 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Task 5: Discussions with WP2, WP3 and WP4 concerning integration issues, including metadata | DSL, KU-LAN, CST | all | 2.5 | 0.6 | 0.3 | 0.1 | 0.3 | 0.2 | 0.1 | 0.1 | 0.4 | 0.3 | 0.1
Task 7: Agreements with owners of existing resources and tools about rights of use and integration. | CST | all | 1.2 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Task 8: Specifications of resource and tool integration. | all | all | 3.9 | 0.7 | 0.4 | 0.2 | 0.5 | 0.3 | 0.2 | 0.3 | 0.4 | 0.7 | 0.2
Task 9: Revision of work plan, according to outcome of task 3-8. | CST | all | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Total T9-T18 |  |  | 10.85 | 3 | 1 | 0.6 | 1.5 | 0.8 | 0.6 | 0.7 | 1.5 | 1.3 | 0.6
Before T28:
Task 0: Coordination (after T28) |  | CST
Task 6: Pilot study/pilot implementation of integration of text resources and text tools |  | CST, DSL, KB
Task 10: Beta version of accessibility modules for speech resources and tools. A tool for acoustically based speech sound analysis is completed in beta-version and tested for source independence on a variety of CLARIN speech resources (e.g. KU-LANCHART and PAROLE, cf. WP3x) |  | CBS, KU-LAN, SDU
Task 11: Beta version of accessibility modules for video resources and perhaps tools |  | SDU, KU-LAN
Task 12: Beta version of accessibility modules for lexical resources |  | AU, DSL, CST
Task 13: Beta version of accessibility modules for NatMus resource. |  | NatMus
Task 14: Beta version of accessibility modules for text resources and tools |  | DSL, KB, KU-INSS, DSN, CST, AU
Task 15: Beta version of accessibility modules, some resources integrated in beta version of platform. Tests and documentation of experiences. |  | all
Before T36:
Task 0: Coordination (T29-T36) |  | CST
Task 16: Resource or tool provider documentation, focus on interoperability/integration |  | all
Task 17: Documentation of test cases |  | all
Task 18: Operational version of accessibility modules and User documentation. |  | all